## Sheet1
RACI Chart
Project Tasks | CEO | EVP Engineering | Industrial Engineer | Flow Optimization Manager | Operations Analyst | Supply Planner | QC Manager | Contract Architect | Civil Subcontractor | EVP Product Development | Marketing Manager | Market Analyst | EVP Finance | Sourcing Manager | Merchant | Risk Analyst | Account Manager | Business Analyst | CPA | Contract Lawyer | Lab Manager | Building Manager | Project Manager | Steering Committee
Phase 1: Research and Analysis
Evaluate Current Workspaces |  |  | C |  | A |  |  | R | [12 empty] | R |  | I | I
Structural and equipment analysis |  |  | A |  | C |  |  |  | R | [13 empty] | I | I
Faculty interview & feedback | I | I | C | C | C |  | C | [15 empty] | R | A
ABC inventory analysis |  |  | C | C | A | R | [14 empty] | R |  | I | I
Current trend analysis |  |  |  | C | [6 empty] | A | R |  |  |  | R | [6 empty] | I | I
Depreciaiton & asset analysis |  |  | C |  | C | [12 empty] | A | R |  |  |  | I | I
Supplier market analysis | [5 empty] | R | [5 empty] | C |  | A | C | R | [6 empty] | I | I
Vendor Analysis | [5 empty] | C |  |  | R |  |  | C |  | A | R | [7 empty] | I | I
Phase 2: Plan
Project charter | I | C | [5 empty] | C | C |  |  |  | C |  |  |  |  | C |  |  |  |  | R | A
Shop floor design & optimization |  |  | A | C | C |  | C | R | C | C | [12 empty] | I | I
Risk Analysis |  | C | C |  | C | C | C | C | C |  |  |  |  | A |  | R |  | C |  | C |  |  | C | I
Inventory Optimization |  |  |  | R | C | [8 empty] | C |  |  | C |  |  |  | R |  | I | I
Inventory Replenishment Planning |  |  |  | C |  | R | [7 empty] | C | A |  | I | I |  |  | R |  |  | I
Budget | C | C |  |  |  | C |  | C | C | C |  |  | A | C |  |  |  |  | R |  |  |  | I | I
Labor Plan |  |  | A |  |  |  |  | R | R | [7 empty] | I | C |  |  |  |  | I | I
Capacity Plan | I | C | R | C | C |  | C | C |  | C |  |  |  | C |  |  | I | [5 empty] | I | I
Construction Plan (From Subcontractor) | I | I | [5 empty] | C | R | [7 empty] | I | [5 empty] | I | I
Plan Approval | A | [8 empty] | C |  |  | R | C |  |  |  | C | C |  |  |  | I | I
Phase 3: Source & Procure
RFx | [5 empty] | C |  |  |  |  | C |  |  | A | R |  | I | C |  |  |  |  | I | I
Supplier selection (TCO, TLC) |  |  | C | C | C | C |  | I | I |  |  |  | C | A | R |  | I | C |  |  |  |  | I | I
Contracting | [12 empty] | A | R |  |  | I |  |  | C |  |  | I | I
Phase 4: Implement
Asset Disposal |  | A | A |  |  |  | C |  | A |  |  |  | C | C |  |  | C |  |  |  |  | R | I | I
Constuction (Outsourced) | I | A | [5 empty] | R | R | [12 empty] | A | I | I
Safety Control |  |  | A |  | C |  | R | [14 empty] | A |  | I
QA & QC |  | C | A |  |  |  | R | [14 empty] | C |  | I
Supplier relationship management | [5 empty] | C | [8 empty] | R |  | A |  |  |  |  | C | I
R - Responsible
A - Accountable
C - Consult
I - Inform